# Fear & Loathing in the Console

## The 37-Week #100Devs Journey

"Buy the ticket, take the ride." The raw path to mastery.

Campaign Start: Tuesday, December 30, 2025
Campaign End: Friday, September 11, 2026

## 🎯 Current Status Assessment

You're currently about 4 weeks into your journey (started around early December based on your Week 5-6 completion status). With the revised timeline starting December 30, 2025, you'll be synchronizing with the official start date.

### What You've Already Accomplished:

- ✅ HTML structure complete

- ✅ CSS fundamentals and advanced styling

- ✅ Flexbox & Grid layouts

- ✅ JavaScript file created with Intersection Observer API

- ✅ Modern, performance-optimized animations

- ⚠️ About section content needs completion

- ⚠️ Diary entries 1-6 need drafting

## Resources to Use Throughout

- MDN Web Docs (HTML/CSS/JS reference)

- JavaScript.info (in-depth JS tutorials)

- freeCodeCamp (practice challenges)

- The Odin Project (comprehensive curriculum)

- Frontend Mentor (practice projects)

- Stack Overflow (problem-solving)

- YouTube (visual learning)

## Success Metrics

By September 11, 2026, you will have:

- ✅ Mastery of HTML, CSS, JavaScript, React

- ✅ Full-stack development skills with MERN stack

- ✅ Live portfolio website with 37 weeks of documented growth

- ✅ Complete, deployed Capstone application

- ✅ Professional online presence (GitHub, LinkedIn)

- ✅ Job-ready skills with portfolio to prove it

## Important Dates to Remember

- 📅 December 30, 2025 - Campaign begins (Week 1)

- 🎊 January 1, 2026 - New Year (Week 1)

- 💘 February 14, 2026 - Valentine's Day (Week 7)

- 🍀 March 17, 2026 - St. Patrick's Day (Week 12)

- 🌸 April 20, 2026 - Spring (Week 16)

- 🎓 May 25, 2026 - Memorial Day (Week 21)

- ☀️ July 4, 2026 - Independence Day (Week 27)

- 📚 August 3, 2026 - Halfway Point (Week 31)

- 🚀 September 11, 2026 - Campaign complete! Job-ready! (Week 37)

## Weekly Habits (Every Week)

### Daily:

- [ ] Code for at least 1-2 hours

- [ ] Commit code to GitHub with descriptive messages

- [ ] Review and refactor previous day's code

### Weekly:

- [ ] Complete all learning objectives for the week

- [ ] Update diary entry with learnings, challenges, and wins

- [ ] Push all code to GitHub

- [ ] Test new features across browsers and devices

- [ ] Participate in developer community (Discord, Reddit, Twitter)

- [ ] Review next week's objectives and prepare

## PHASE I: Frontend Foundation (Weeks 1-6)

### Week 1: HTML Foundations & Project Setup

Dates: December 30, 2025 - January 5, 2026

Technical Learning:

- HTML5 semantic elements (header, nav, main, section, article, footer)

- Document structure, meta tags, and accessibility basics

- File organization and naming conventions

- Git basics: init, add, commit, push

Portfolio Actions:

- [ ] Set up project repository on GitHub

- [ ] Create root index.html with proper DOCTYPE and meta tags

- [ ] Build basic HTML structure: header, navigation, hero section, main content areas, footer

- [ ] Create /diary/ folder and generate 37 empty HTML files (week-01.html through week-37.html)

- [ ] Create /capstone/ folder with empty files: index.html, deep-dive.html, design-ux.html

- [ ] Create /assets/ folder structure: /img/, /css/, /js/

- [ ] Initialize README.md with project description

- [ ] Make first Git commit and push to GitHub

Deliverables: Complete file structure, GitHub repo initialized, all HTML skeleton files created

Diary Entry:

- [ ] Draft/Ready to Push: Week 1 diary entry (week-01.html)

### Week 2: CSS Fundamentals & Visual Design

Dates: January 6-12, 2026

Technical Learning:

- CSS syntax, selectors, specificity, and the cascade

- Box model (margin, border, padding, content)

- Typography fundamentals (font families, sizes, line-height, letter-spacing)

- Color theory and color systems (hex, RGB, HSL)

- CSS variables for theming

Portfolio Actions:

- [ ] Create assets/css/main.css and link to all HTML pages

- [ ] Define color palette (primary, secondary, accent, neutrals) using CSS variables

- [ ] Select and import fonts (Google Fonts or similar)

- [ ] Style typography system: headings (h1-h6), paragraphs, links, lists

- [ ] Apply box model to create visual hierarchy

- [ ] Create /assets/img/ subfolders: /hero/, /about/, /diary/, /capstone/

- [ ] Source placeholder images for hero section

- [ ] Begin designing logo or personal brand mark

Deliverables: CSS file with variables, typography system, initial styling applied to index.html

Diary Entry:

- [ ] Draft/Ready to Push: Week 2 diary entry (week-02.html)

### Week 3: Flexbox & Grid Layouts

Dates: January 13-19, 2026

Technical Learning:

- CSS Flexbox: flex containers, flex items, justify-content, align-items, flex-wrap

- CSS Grid: grid-template-columns, grid-template-rows, gap, grid areas

- Layout patterns and when to use Flexbox vs Grid

- Responsive design principles

Portfolio Actions:

- [ ] Implement flexbox for navigation bar (horizontal menu)

- [ ] Create responsive hero section with centered content

- [ ] Build About section layout using flexbox (image + text side-by-side)

- [ ] Design card layout for diary log entries using CSS Grid

- [ ] Create footer layout with Grid

- [ ] Experiment with both Flexbox and Grid to understand their strengths

Deliverables: Multi-layout homepage using both Flexbox and Grid

Diary Entry:

- [ ] Draft/Ready to Push: Week 3 diary entry (week-03.html)

### Week 4: Responsive Design & Media Queries

Dates: January 20-26, 2026

Technical Learning:

- Mobile-first approach

- Media queries and breakpoints

- Responsive units (rem, em, %, vw, vh)

- Responsive images and srcset

- Testing responsive designs

Portfolio Actions:

- [ ] Add media queries for tablet (768px) and mobile (480px) breakpoints

- [ ] Implement mobile-first CSS architecture

- [ ] Test responsiveness on multiple screen sizes using browser dev tools

- [ ] Optimize navigation for mobile (prepare for hamburger menu)

- [ ] Ensure all content is readable on small screens

- [ ] Add responsive images with proper sizing

Deliverables: Fully responsive homepage layout working on all screen sizes

Diary Entry:

- [ ] Draft/Ready to Push: Week 4 diary entry (week-04.html)

### Week 5: Advanced CSS & Animations

Dates: January 27 - February 2, 2026

Technical Learning:

- CSS positioning (relative, absolute, fixed, sticky)

- Transitions and animations

- Transform properties (translate, rotate, scale)

- Keyframe animations

- Pseudo-classes and pseudo-elements

Portfolio Actions:

- [ ] Add hover effects and transitions to navigation and buttons

- [ ] Implement sticky navigation bar

- [ ] Create scroll-triggered animations

- [ ] Add loading animations

- [ ] Style buttons with hover and active states

- [ ] Create reusable animation classes

Deliverables: Polished, animated interface with smooth transitions

Diary Entry:

- [ ] Draft/Ready to Push: Week 5 diary entry (week-05.html)

### Week 6: CSS Best Practices & Component Building

Dates: February 3-9, 2026

Technical Learning:

- CSS organization methodologies (BEM, SMACSS)

- Component-based CSS architecture

- CSS custom properties advanced usage

- Performance optimization

- Browser compatibility

Portfolio Actions:

- [ ] Create reusable CSS components: buttons, cards, form inputs

- [ ] Style the footer with social links and contact information

- [ ] Create /spells/ and /graveyard/ folders with empty index.html files

- [ ] Design and implement page headers for all sections

- [ ] Finalize color scheme and ensure consistent styling across all pages

- [ ] Create style guide document listing all colors, fonts, and component styles

- [ ] Add favicon and meta tags for social sharing

- [ ] Gather all images needed for About section

Deliverables: Complete component library, style guide, consistent aesthetic across all pages

Diary Entry:

- [ ] Draft/Ready to Push: Week 6 diary entry (week-06.html)

## PHASE II: JavaScript Fundamentals (Weeks 7-12)

### Week 7: JavaScript Basics I

Dates: February 10-16, 2026

Technical Learning:

- JavaScript fundamentals: variables (let, const, var)

- Data types: strings, numbers, booleans, null, undefined

- Operators: arithmetic, comparison, logical

- Type coercion and conversion

- Template literals

Portfolio Actions:

- [ ] Create assets/js/main.js and link to all HTML pages

- [ ] Write JavaScript to log information to console

- [ ] Create variables to store portfolio data

- [ ] Practice string manipulation for dynamic content

- [ ] Add console logs to track page interactions for debugging practice

- [ ] Draft About section content (300-500 words about your journey, goals, and background)

Deliverables: JavaScript file structure, About section content completed

Diary Entry:

- [ ] Draft/Ready to Push: Week 7 diary entry (week-07.html)

### Week 8: JavaScript Basics II

Dates: February 17-23, 2026

Technical Learning:

- Control flow: if/else statements, switch, ternary operators

- Comparison and logical operators

- Truthy and falsy values

- Conditional rendering concepts

Portfolio Actions:

- [ ] Implement conditional logic for UI features

- [ ] Create dark/light mode toggle logic (prepare for implementation)

- [ ] Add conditional styling based on user interactions

- [ ] Write professional bio focusing on transition to development

- [ ] List technical skills and interests

Deliverables: Conditional logic implemented, professional bio complete

Diary Entry:

- [ ] Draft/Ready to Push: Week 8 diary entry (week-08.html)

### Week 9: Functions

Dates: February 24 - March 2, 2026

Technical Learning:

- Function declarations vs expressions

- Arrow functions

- Parameters and arguments

- Return values

- Function scope

- Default parameters

Portfolio Actions:

- [ ] Create utility functions for common tasks

- [ ] Implement scroll-to-top button with function

- [ ] Create helper functions for DOM manipulation

- [ ] Organize code into reusable functions

- [ ] Create /assets/js/utils/ folder for utility functions

Deliverables: Function-based code architecture, utility functions library

Diary Entry:

- [ ] Draft/Ready to Push: Week 9 diary entry (week-09.html)

### Week 10: Arrays & Objects

Dates: March 3-9, 2026

Technical Learning:

- Array fundamentals: creating, accessing, modifying

- Array methods: push, pop, shift, unshift, splice

- Objects: creating, accessing properties, methods

- Object destructuring

- JSON format

Portfolio Actions:

- [ ] Create array of project data

- [ ] Create object structure for diary entries

- [ ] Store portfolio information in objects

- [ ] Practice accessing and manipulating data structures

- [ ] Draft diary entries for Weeks 1-6

Deliverables: Data structures for portfolio content, first 6 diary entries drafted

Diary Entry:

- [ ] Draft/Ready to Push: Week 10 diary entry (week-10.html)

### Week 11: DOM Manipulation I

Dates: March 10-16, 2026

Technical Learning:

- The Document Object Model (DOM)

- Selecting elements: getElementById, querySelector, querySelectorAll

- Changing content: textContent, innerHTML

- Modifying attributes

- Changing styles

Portfolio Actions:

- [ ] Select and manipulate DOM elements

- [ ] Change text content dynamically

- [ ] Update element attributes

- [ ] Modify inline styles with JavaScript

- [ ] Create dynamic content based on data

Deliverables: Dynamic content manipulation, interactive text updates

Diary Entry:

- [ ] Draft/Ready to Push: Week 11 diary entry (week-11.html)

### Week 12: DOM Manipulation II & Events

Dates: March 17-23, 2026

Technical Learning:

- Creating and removing elements

- Event listeners and event handling

- Event object and event properties

- Event bubbling and delegation

- Common events: click, submit, scroll, load

Portfolio Actions:

- [ ] Implement hamburger menu toggle for mobile navigation

- [ ] Add smooth scroll behavior to navigation links

- [ ] Create interactive features with event listeners

- [ ] Add GitHub repository links to diary entries

- [ ] Implement form validation for contact form (basic)

- [ ] Draft diary entries for Weeks 7-12

Deliverables: Interactive navigation, event-driven features, weeks 7-12 diary entries

Diary Entry:

- [ ] Draft/Ready to Push: Week 12 diary entry (week-12.html)

## PHASE III: Advanced JavaScript (Weeks 13-18)

### Week 13: Array Methods & Iteration

Dates: March 24-30, 2026

Technical Learning:

- Higher-order functions

- Array methods: forEach, map, filter, reduce

- find, some, every methods

- Chaining array methods

- When to use each method

Portfolio Actions:

- [ ] Create JSON file with diary entry data structure

- [ ] Use map() to generate diary entry cards dynamically

- [ ] Filter diary entries by category/tag

- [ ] Implement search functionality using filter()

- [ ] Refactor diary entry generation to pull from JSON

Deliverables: Dynamic diary generation from data, search/filter functionality

Diary Entry:

- [ ] Draft/Ready to Push: Week 13 diary entry (week-13.html)

### Week 14: Advanced Functions & Scope

Dates: March 31 - April 6, 2026

Technical Learning:

- Closures and lexical scope

- Callback functions

- Higher-order functions deep dive

- IIFE (Immediately Invoked Function Expressions)

- Function composition

Portfolio Actions:

- [ ] Refactor code to use closures for data privacy

- [ ] Implement callback functions for async-like operations

- [ ] Create modular code with proper scope management

- [ ] Organize JavaScript into logical modules

- [ ] Draft diary entries for Weeks 13-18

Deliverables: Modular, well-scoped JavaScript architecture

Diary Entry:

- [ ] Draft/Ready to Push: Week 14 diary entry (week-14.html)

### Week 15: ES6+ Features

Dates: April 7-13, 2026

Technical Learning:

- Destructuring (arrays and objects)

- Spread and rest operators

- Default parameters

- Enhanced object literals

- for...of loops

Portfolio Actions:

- [ ] Refactor code to use destructuring

- [ ] Implement spread operator for array/object manipulation

- [ ] Use enhanced object literals for cleaner code

- [ ] Update all JavaScript to modern ES6+ syntax

- [ ] Add tags/categories to diary entries

Deliverables: Modern ES6+ codebase, categorized diary entries

Diary Entry:

- [ ] Draft/Ready to Push: Week 15 diary entry (week-15.html)

### Week 16: Debugging & Error Handling

Dates: April 14-20, 2026

Technical Learning:

- Browser developer tools

- Console methods: log, error, warn, table

- Debugging techniques

- try...catch blocks

- Error types and error handling

Portfolio Actions:

- [ ] Add comprehensive error handling to all JavaScript

- [ ] Implement try...catch for user interactions

- [ ] Add helpful error messages

- [ ] Debug and fix any existing issues

- [ ] Add console warnings for development

Deliverables: Robust error handling, debugged codebase

Diary Entry:

- [ ] Draft/Ready to Push: Week 16 diary entry (week-16.html)

### Week 17: Local Storage & Browser APIs

Dates: April 21-27, 2026

Technical Learning:

- localStorage and sessionStorage

- Storing and retrieving data

- JSON.stringify and JSON.parse

- Browser storage limitations

- Storage events

Portfolio Actions:

- [ ] Implement dark/light mode toggle with localStorage persistence

- [ ] Save user preferences

- [ ] Store form data temporarily

- [ ] Create settings panel for user preferences

- [ ] Add user preference persistence across sessions

Deliverables: Persistent user preferences, dark mode implementation

Diary Entry:

- [ ] Draft/Ready to Push: Week 17 diary entry (week-17.html)

### Week 18: Asynchronous JavaScript I

Dates: April 28 - May 4, 2026

Technical Learning:

- Synchronous vs asynchronous code

- setTimeout and setInterval

- Callbacks and callback hell

- Introduction to Promises

- Understanding the event loop

Portfolio Actions:

- [ ] Add loading animations with setTimeout

- [ ] Implement delayed UI updates

- [ ] Create timed transitions

- [ ] Add animations triggered by timers

- [ ] Draft diary entries for Weeks 19-24

Deliverables: Timed animations, understanding of async concepts

Diary Entry:

- [ ] Draft/Ready to Push: Week 18 diary entry (week-18.html)

## PHASE IV: APIs & Modern JavaScript (Weeks 19-24)

### Week 19: Promises & Async/Await

Dates: May 5-11, 2026

Technical Learning:

- Promise creation and consumption

- .then(), .catch(), .finally()

- Promise.all() and Promise.race()

- async/await syntax

- Error handling with async/await

Portfolio Actions:

- [ ] Refactor callback code to use Promises

- [ ] Implement async functions

- [ ] Add loading states for async operations

- [ ] Create utility functions for async operations

- [ ] Handle errors gracefully with async/await

Deliverables: Promise-based async code, modern async patterns

Diary Entry:

- [ ] Draft/Ready to Push: Week 19 diary entry (week-19.html)

### Week 20: Fetch API & HTTP Requests

Dates: May 12-18, 2026

Technical Learning:

- HTTP methods (GET, POST, PUT, DELETE)

- Fetch API syntax

- Request and response objects

- HTTP status codes

- Headers and CORS basics

Portfolio Actions:

- [ ] Implement email service integration (EmailJS or FormSubmit) for contact form

- [ ] Add loading spinner during async operations

- [ ] Create success/error notifications

- [ ] Test form submission thoroughly

- [ ] Add form validation before submission

Deliverables: Working contact form with email integration

Diary Entry:

- [ ] Draft/Ready to Push: Week 20 diary entry (week-20.html)

### Week 21: Working with External APIs

Dates: May 19-25, 2026

Technical Learning:

- REST API concepts

- API authentication (API keys)

- Reading API documentation

- Handling API responses

- Rate limiting awareness

Portfolio Actions:

- [ ] Integrate GitHub API to display your repositories

- [ ] Create "Latest Projects" section pulling from GitHub

- [ ] Display GitHub contribution stats

- [ ] Add error handling for API failures

- [ ] Implement fallback UI when API is unavailable

Deliverables: GitHub API integration, dynamic project showcase

Diary Entry:

- [ ] Draft/Ready to Push: Week 21 diary entry (week-21.html)

### Week 22: Modern JavaScript Patterns

Dates: May 26 - June 1, 2026

Technical Learning:

- Module pattern

- Revealing module pattern

- ES6 modules (import/export)

- Separation of concerns

- Code organization best practices

Portfolio Actions:

- [ ] Refactor JavaScript into separate module files

- [ ] Create modules: navigation.js, diary.js, api.js, utils.js

- [ ] Use import/export for module dependencies

- [ ] Organize code by feature/responsibility

- [ ] Draft diary entries for Weeks 25-30

Deliverables: Modular JavaScript architecture with ES6 modules

Diary Entry:

- [ ] Draft/Ready to Push: Week 22 diary entry (week-22.html)

### Week 23: Object-Oriented JavaScript

Dates: June 2-8, 2026

Technical Learning:

- Constructor functions

- Prototypes and prototype chain

- ES6 Classes

- Inheritance and extends

- Static methods

Portfolio Actions:

- [ ] Create classes for portfolio components

- [ ] Implement class-based architecture for diary entries

- [ ] Use inheritance for related components

- [ ] Refactor procedural code to OOP where appropriate

- [ ] Create reusable class components

Deliverables: Object-oriented portfolio architecture

Diary Entry:

- [ ] Draft/Ready to Push: Week 23 diary entry (week-23.html)

### Week 24: Performance & Optimization

Dates: June 9-15, 2026

Technical Learning:

- Performance optimization techniques

- Debouncing and throttling

- Lazy loading

- Code splitting concepts

- Image optimization

Portfolio Actions:

- [ ] Implement debouncing for search functionality

- [ ] Add lazy loading for images

- [ ] Optimize JavaScript bundle size

- [ ] Improve page load performance

- [ ] Audit and optimize CSS

- [ ] Run Lighthouse audits and improve scores

Deliverables: Optimized, performant portfolio

Diary Entry:

- [ ] Draft/Ready to Push: Week 24 diary entry (week-24.html)

## PHASE V: React & Modern Frontend (Weeks 25-31)

### Week 25: React Foundations

Dates: June 16-22, 2026

Technical Learning:

- React philosophy and virtual DOM

- JSX syntax

- Components and props

- Create React App / Vite setup

- React Developer Tools

Portfolio Actions:

- [ ] Set up React development environment

- [ ] Create first React components

- [ ] Build component library: Button, Card, Navigation

- [ ] Understand component composition

- [ ] Convert one section of portfolio to React (experimental)

Deliverables: React environment setup, basic component library

Diary Entry:

- [ ] Draft/Ready to Push: Week 25 diary entry (week-25.html)

### Week 26: React State & Hooks

Dates: June 23-29, 2026

Technical Learning:

- useState hook

- State management basics

- Event handling in React

- Controlled components

- Lifting state up

Portfolio Actions:

- [ ] Implement stateful components

- [ ] Create interactive React components

- [ ] Build form components with state

- [ ] Manage component state effectively

- [ ] Create toggle components (dark mode, menu)

Deliverables: Stateful React components, interactive UI

Diary Entry:

- [ ] Draft/Ready to Push: Week 26 diary entry (week-26.html)

### Week 27: React Effects & Side Effects

Dates: June 30 - July 6, 2026

Technical Learning:

- useEffect hook

- Effect dependencies

- Cleanup functions

- Data fetching with useEffect

- Effect best practices

Portfolio Actions:

- [ ] Implement useEffect for side effects

- [ ] Fetch data from APIs in React

- [ ] Handle component lifecycle events

- [ ] Add document title updates

- [ ] Implement scroll effects with useEffect

- [ ] Draft diary entries for Weeks 31-37

Deliverables: React components with effects, API integration

Diary Entry:

- [ ] Draft/Ready to Push: Week 27 diary entry (week-27.html)

### Week 28: React Router & Navigation

Dates: July 7-13, 2026

Technical Learning:

- React Router setup

- Routes and Route components

- Link and NavLink

- URL parameters

- Programmatic navigation

Portfolio Actions:

- [ ] Install and configure React Router

- [ ] Create routes for all portfolio pages

- [ ] Implement navigation with Link components

- [ ] Add active link styling

- [ ] Create 404 page

- [ ] Implement nested routes

Deliverables: Multi-page React application with routing

Diary Entry:

- [ ] Draft/Ready to Push: Week 28 diary entry (week-28.html)

### Week 29: Advanced React Patterns

Dates: July 14-20, 2026

Technical Learning:

- Custom hooks

- useContext for global state

- useReducer for complex state

- Composition patterns

- Render props and HOCs (overview)

Portfolio Actions:

- [ ] Create custom hooks for reusable logic

- [ ] Implement context for theme management

- [ ] Use useReducer for complex state

- [ ] Refactor components to use custom hooks

- [ ] Create /spells/ content: "React Patterns & Hooks I've Mastered"

Deliverables: Advanced React patterns implemented, Spells page started

Diary Entry:

- [ ] Draft/Ready to Push: Week 29 diary entry (week-29.html)

### Week 30: React Performance & Optimization

Dates: July 21-27, 2026

Technical Learning:

- React.memo and useMemo

- useCallback hook

- Code splitting with React.lazy

- Suspense boundaries

- Performance profiling

Portfolio Actions:

- [ ] Optimize component re-renders

- [ ] Implement code splitting

- [ ] Add loading states with Suspense

- [ ] Profile and optimize React app

- [ ] Lazy load routes and components

Deliverables: Optimized React application

Diary Entry:

- [ ] Draft/Ready to Push: Week 30 diary entry (week-30.html)

### Week 31: React Forms & Validation

Dates: July 28 - August 3, 2026

Technical Learning:

- Controlled vs uncontrolled components

- Form libraries (React Hook Form or Formik)

- Form validation patterns

- Error handling in forms

- Form submission

Portfolio Actions:

- [ ] Build comprehensive contact form in React

- [ ] Implement form validation

- [ ] Add error messages and success states

- [ ] Create reusable form components

- [ ] Handle form submission with API

Deliverables: Production-ready contact form in React

Diary Entry:

- [ ] Draft/Ready to Push: Week 31 diary entry (week-31.html)

## PHASE VI: Backend & Full-Stack (Weeks 32-37)

### Week 32: Node.js Fundamentals

Dates: August 4-10, 2026

Technical Learning:

- Node.js runtime and npm

- CommonJS modules

- Node core modules (fs, path, http)

- Package.json and dependencies

- Environment variables

Portfolio Actions:

- [ ] Install Node.js and verify setup

- [ ] Create Node.js project with npm init

- [ ] Build basic HTTP server

- [ ] Set up backend folder structure

- [ ] Configure environment variables

Deliverables: Node.js environment configured, basic server running

Diary Entry:

- [ ] Draft/Ready to Push: Week 32 diary entry (week-32.html)

### Week 33: Express.js & RESTful APIs

Dates: August 11-17, 2026

Technical Learning:

- Express.js framework

- Routing and middleware

- RESTful API design principles

- Request/response cycle

- Error handling middleware

Portfolio Actions:

- [ ] Install Express.js

- [ ] Create Express server

- [ ] Build API routes: /api/contact, /api/projects

- [ ] Implement middleware (CORS, body-parser)

- [ ] Test API with Postman/Thunder Client

- [ ] Create API documentation

Deliverables: Express API with RESTful endpoints

Diary Entry:

- [ ] Draft/Ready to Push: Week 33 diary entry (week-33.html)

### Week 34: MongoDB & Databases

Dates: August 18-24, 2026

Technical Learning:

- NoSQL vs SQL databases

- MongoDB concepts

- Mongoose ODM

- Schema design

- CRUD operations

Portfolio Actions:

- [ ] Set up MongoDB Atlas account

- [ ] Connect Node.js to MongoDB

- [ ] Create Mongoose schemas (Contact, Project)

- [ ] Implement database CRUD operations

- [ ] Test database integration

- [ ] Create database seed data

Deliverables: MongoDB connected, schemas created, CRUD operations working

Diary Entry:

- [ ] Draft/Ready to Push: Week 34 diary entry (week-34.html)

### Week 35: Full-Stack Integration

Dates: August 25-31, 2026

Technical Learning:

- Connecting React frontend to Express backend

- Proxy configuration

- Environment variables in React

- CORS configuration

- Full-stack architecture

Portfolio Actions:

- [ ] Connect React app to Express API

- [ ] Implement full-stack contact form

- [ ] Display dynamic data from database

- [ ] Handle API errors in frontend

- [ ] Test full-stack application

- [ ] Complete /graveyard/ page: "Failed Experiments & Lessons Learned"

Deliverables: Full-stack portfolio with database integration, Graveyard page complete

Diary Entry:

- [ ] Draft/Ready to Push: Week 35 diary entry (week-35.html)

### Week 36: Deployment & DevOps

Dates: September 1-7, 2026

Technical Learning:

- Deployment platforms

- Environment configuration

- Build processes

- CI/CD basics

- Monitoring and logging

Portfolio Actions:

- [ ] Prepare production build of React app

- [ ] Deploy backend to Render/Railway/Heroku

- [ ] Deploy frontend to Vercel/Netlify

- [ ] Configure environment variables on hosting

- [ ] Set up custom domain (optional)

- [ ] Configure SSL certificates

- [ ] 🚀 PORTFOLIO IS LIVE! 🚀

Deliverables: Portfolio deployed and accessible online

Diary Entry:

- [ ] Draft/Ready to Push: Week 36 diary entry (week-36.html)

### Week 37: Final Polish & Launch

Dates: September 8-11, 2026 (FINAL WEEK!)

Technical Learning:

- Portfolio best practices

- Technical writing

- README creation

- Professional presentation

Portfolio Actions:

- [ ] Complete all 37 diary entries

- [ ] Finalize About section

- [ ] Create comprehensive resume (PDF)

- [ ] Update LinkedIn profile

- [ ] Polish all GitHub repositories with READMEs

- [ ] Add Open Graph meta tags

- [ ] Create demo video walkthrough

- [ ] Write blog post about your journey

- [ ] Share portfolio on social media

- [ ] Apply to 5+ developer positions

- [ ] 🎓 FRIDAY, SEPTEMBER 11, 2026 - GRADUATION DAY! 🎓

Final Deliverables:

- ✅ Complete, deployed portfolio website

- ✅ Full-stack application with database

- ✅ 37 detailed diary entries

- ✅ Professional resume and LinkedIn

- ✅ Well-documented GitHub profile

- ✅ Job-ready developer skills

Diary Entry:

- [ ] Draft/Ready to Push: Week 37 diary entry (week-37.html)

## 🏆 Congratulations, Graduate! 🏆

You did it! 37 weeks of relentless learning, building, and growth. You're now a full-stack developer with the portfolio to prove it. Time to land that job and change your life. The ride was wild, but you bought the ticket and made it to the end. Now go show the world what